## Time sceduale
Projektplan Draft C1 (NetStation to all countries)
| Produkt Center | Responsible | SE |  | NO |  | FI |  | DK |  | SL
Uge 47 | C1 English version | HL/MO
Uge 48 | C1 New functionality design | HL/MO | Translation begins | ? | Input to New functions | ? | Input to New functions | ? | Input to New functions | ME
Uge 49 | C1 New functionality design | HL/MO | Translation ends | ?
Uge 50 | C1 New functions implementation | HL/MO/LL |  |  |  |  | Translation begins | ? |  |  | SL access to Internal web
| SE. Version design | MO/HL | Editorial pages | ?
| SE: HW/SW test environment | NW/SN
Uge 51 | SE ready for int. Test | all | Remote test | ?
Uge 1 | SE: HW/SW Moved to local | NW/SN | HW arrives/SW installation | TECH
Uge 2 | SE Siteintegration (CIS ?) | LL/MO/? | Education | ? |  |  | Translation ends | ?
Uge 3 |  |  | Online test | ?
Uge 4 | SE Launch | all | LAUNCH | ?
Uge 5 | FI. Version design | MO/HL |  |  | Translation begins |  | Editorial pages | ?
Uge 6 | FI. ready for int. Test | all |  |  |  |  | Remote test | ?
Uge 7 | FI: HW/SW Moved to local | NW/SN |  |  |  |  | HW arrives/SW installation | ?
Uge 8 | FI Siteintegration (CIS ?) | [5 empty] | Education | ?
Uge 9 | [6 empty] | Online test | ?
Uge 10 | FI Launch |  |  |  | Translation ends |  | LAUNCH | ?
Uge 11 | NO. Version design | MO/HL |  |  | Editorial pages | ?
Uge 12 | NO. ready for int. Test | all |  |  | Remote test | ?
Uge 13 | NO: HW/SW Moved to local | NW/SN |  |  | HW arrives/SW installation | ?
Uge 14 | NO Siteintegration (CIS ?) |  |  |  | Education | ?
Uge 15 |  |  |  |  | Online test | ?
Uge 16 | NO Launch |  |  |  | LAUNCH | ?
Uge 17
Uge 18
Uge 19
Uge 20
Uge 21
Uge 22
Uge 23
Uge 24
Uge 25

## Persons
Persons involved
Produkt Center
HL | Henrik Leschly
MO | Morten Oreby
LL | Lasse Løvdahl
SN | Stubbe Nielsen
KP | Klaus Philkjær
NW | Niels W. Kristiansen
SE
NO
FI
DK